Pharma AI & Data Congress

Mumbai | 21 May 2026

A GPACTS 2026 Series Event

Event Operations Brief

Confidential — Internal Use Only

# SECTION 1: Event Overview

Full-day conference (9 AM – 6:30 PM) focused on Track 1: AI, Data & Intelligent Automation in pharma

- Venue: Mumbai (TBD — target 5-star hotel conference facility in BKC/Lower Parel/Powai corridor)

- Expected delegates: 80–120 pharma IT leaders

- Theme: From Data to Decisions: AI-Powered Pharma

- Why Mumbai first: Highest concentration of pharma HQs (Sun Pharma, Cipla, Lupin, Alkem, Glenmark, Piramal). Natural starting point for CIO/CDO outreach. AI/Data theme has highest market demand score (76/80)

# SECTION 2: Proposed Agenda

Detailed Event Timetable

| Time | Session | Format | Speaker Slot |
| --- | --- | --- | --- |
| 09:00–09:30 | Registration & Networking Breakfast | — | — |
| 09:30–09:45 | Welcome & Opening Remarks | Address | GPACTS Host |
| 09:45–10:15 | Keynote: Enterprise AI Strategy for Indian Pharma — From Pilot to Scale | Keynote (30 min) | P1 CIO/CDO |
| 10:15–10:45 | Keynote: The ISPE GAMP AI Guide — What Pharma IT Must Know | Keynote (30 min) | P1 Regulatory/ISPE Expert |
| 10:45–11:00 | Networking & Refreshment Break | — | — |
| 11:00–11:45 | Panel: Data Governance in Regulated Environments — ALCOA++ Meets Data Mesh | Panel (45 min) | 4 panellists + moderator |
| 11:45–12:15 | Practitioner Talk: Implementing Predictive Quality & Yield Optimisation | Case Study (30 min) | P1/P2 |
| 12:15–12:45 | Fireside Chat: GenAI in Pharma — Hype vs Reality | Fireside (30 min) | CIO + Industry Analyst |
| 12:45–13:45 | Networking Lunch | — | Sponsor activation |
| 13:45–14:15 | Sponsor Keynote / Workshop | Sponsored Session (30 min) | Title/Platinum Sponsor |
| 14:15–15:00 | Panel: Building AI Talent & Culture in Pharma Organisations | Panel (45 min) | 4 panellists |
| 15:00–15:30 | Practitioner Talk: AI-Powered Drug Discovery & Clinical Trial Optimisation | Case Study (30 min) | P2 |
| 15:30–15:45 | Networking & Refreshment Break | — | — |
| 15:45–16:30 | Roundtable: CIO-CDO Dialogue — Aligning Data Strategy with Business Outcomes | Closed Roundtable (45 min) | CXO invite-only |
| 16:30–17:00 | Practitioner Talk: RPA & Intelligent Automation in Pharma Supply Chain | Case Study (30 min) | P2 |
| 17:00–17:30 | Closing Keynote: The Future of Pharma IT — 2030 Vision | Keynote (30 min) | Industry thought leader |
| 17:30–17:45 | Vote of Thanks & Closing | Address | GPACTS Host |
| 17:45–18:30 | Networking Reception & Cocktails | — | Sponsor-hosted |

# SECTION 3: Speaker Targets (Mumbai-Specific)

| Name | Designation | Company | Role at Event | Priority | Status |
| --- | --- | --- | --- | --- | --- |
| Dheeraj Sinha | EVP & Global CIO | Sun Pharmaceutical | Opening Keynote | P1 | To Approach |
| Narendra K Saini | CDO | Lupin Ltd | Practitioner Keynote | P1 | To Approach |
| Ganesh Ramachandran | Global CIO | Alkem Laboratories | Panel Moderator | P1 | To Approach |
| Sumit Garg | Global CIO | Piramal Pharma | Panel: AI in CDMO | P1 | To Approach |
| Sanjay Nandavadekar | Director IT | Cipla | Panel: Digital Transformation | P1 | To Approach |
| [CDO to identify] | CDO/Head Data | Dr. Reddy's / Zydus | Data Governance Panel | P2 | Research Needed |
| [AI/ML Head] | Head of AI/ML | Biocon / Glenmark | Practitioner Talk | P2 | Research Needed |
| Dr. Ajay Babu Pazhayattil | ISPE Expert | Industry advisor | GAMP AI Guide Keynote | P1 | To Approach |
| [Sponsor Speaker] | CTO/VP | AI/Data Vendor | Sponsor Keynote | P2 | Tied to Sponsorship |

# SECTION 4: Sponsor Strategy (Mumbai-Specific)

Target: 3–5 sponsors | Revenue target: ₹8–15L

Priority sponsor categories for AI & Data theme:

| Category | Target Companies | Fit | Approach |
| --- | --- | --- | --- |
| AI/Data Platforms | Databricks, Snowflake, Informatica, Palantir, Dataiku, SAS | Primary fit (Track 1 core) | Solution demo + keynote slot |
| Cloud Providers | AWS, Microsoft Azure, Google Cloud | Strong fit (AI runs on cloud) | AI-on-cloud positioning |
| IT Services (AI Practice) | TCS, Infosys, Wipro, HCLTech, LTIMindtree | Good fit (pharma AI implementations) | Case study slot |
| RPA/Automation | UiPath, Automation Anywhere | Good fit (intelligent automation) | Workshop slot |

# SECTION 5: Delegate Acquisition Plan (Mumbai)

Target: 80–120 delegates, minimum 60% pharma end-users (not vendors)

- C-Suite/VP target: 25%+ of total

- Primary target titles: CIO, CDO, Head of Data & Analytics, Head of AI/ML, VP Digital Innovation, IT Directors

- Secondary: Cloud Architects, Data Engineers, Data Scientists (practitioner-level)

- Mumbai-based priority companies: Sun Pharma, Cipla, Lupin, Alkem, Glenmark, Piramal, Ajanta, Wockhardt, Indoco, Abbott India, Pfizer India, Novartis India, Sanofi India

Acquisition Timeline:

| Week | Action | Target |
| --- | --- | --- |
| W1-W2 (Now) | Build Mumbai pharma IT contact list, 200+ names | Database ready |
| W3 | Launch email campaign #1 (save the date), first LinkedIn outreach wave | Email sent to 200+ |
| W4 | Speaker announcements + email campaign #2, telecalling begins | 30+ confirmations |
| W5-W6 | Early bird deadline push, referral programme launch | 50+ paid registrations |
| W7 | Final push, agenda reveal email, personal CXO invitations | 70+ confirmations |
| W8 (21 May) | EVENT DAY — target 80+ confirmed, 60+ attended | Attendance: 60+ |

# SECTION 6: Budget Estimate (Mumbai)

| Cost Head | Low Estimate | High Estimate | Notes |
| --- | --- | --- | --- |
| Venue & F&B | ₹3L | ₹5L | 5-star hotel, full-day package, 100-120 pax |
| Speaker Travel & Accommodation | ₹1L | ₹2L | Most speakers Mumbai-based; 2-3 outstation |
| AV & Production | ₹1.5L | ₹2.5L | Stage, screens, sound, recording, confidence monitors |
| Marketing & Promotion | ₹2L | ₹3L | Digital ads, email tools, design, printed collateral |
| Technology | ₹1L | ₹1.5L | Registration platform, event app, badge printing |
| Delegate Kits & Branding | ₹0.5L | ₹1L | Bags, notepads, stage backdrop, standees |
| Miscellaneous (10%) | ₹0.9L | ₹1.5L | Buffer |
| TOTAL | ₹9.9L | ₹16.5L | Overall budget range |
| Revenue target | ₹8–15L | Sponsorship | + ₹2–5L (paid delegate passes) |
| Break-even | 3 sponsors | Gold level | + 30 paid delegates |

# SECTION 7: Week-by-Week Action Plan

| Week | Speaker Team | Sponsor Team | Delegate Team | Marketing Team | Tech Team |
| --- | --- | --- | --- | --- | --- |
| W1-W2 | Finalise speaker shortlist, outreach to P1 | Sponsor deck ready, begin outreach | Build contact database | Visual identity, website design | Evaluate registration platforms |
| W3-W4 | Secure 3-4 speakers, pursue rest | Close 1-2 sponsors | Launch email + LinkedIn | Website live, first campaigns | Registration system live |
| W5-W6 | All speakers confirmed, collect bios/photos | Close remaining sponsors | Early bird push, telecalls | Speaker announcements, agenda teaser | Event app setup |
| W7 | Speaker briefing, collect presentations | Sponsor fulfilment prep | Final push, CXO personal invites | Full agenda publish, final emails | AV vendor confirmed, dry run plan |
| W8 (21 May) | Speaker management, green room | Sponsor booth setup | On-site registration | Live coverage, media | Full tech ops |

# SECTION 8: Venue Requirements

- Location: BKC / Lower Parel / Powai / Andheri East corridor (accessible to pharma HQs)

- Capacity: Main hall for 120 pax (theatre style) with ability to convert to roundtable for 30

- Breakout room: 1 room for 30 pax (sponsor workshop / CXO roundtable)

- AV: Built-in projector, 2 screens, professional sound system, 4+ wireless mics, recording capability

- F&B: Breakfast, 2 tea/coffee breaks, sit-down lunch, evening cocktails

- Wi-Fi: High-speed, dedicated event SSID

- Branding: Permission for backdrop, standees, roll-ups at entrance and stage

- Parking: Adequate for 30-40 vehicles

- Budget range: ₹3-5L for full-day package

# SECTION 9: Success Metrics

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Total attendance | 80+ | Registration system |
| C-Suite/VP ratio | >25% | Badge category analysis |
| Speaker NPS | >8.5/10 | Post-event survey |
| Delegate NPS | >8.0/10 | Post-event survey |
| Sponsor satisfaction | >8.0/10 | Sponsor feedback form |
| Leads generated for sponsors | 50+ per sponsor | Lead capture system |
| Social media impressions | 50,000+ | LinkedIn analytics |
| Pipeline for Ahmedabad | 20+ warm leads | CRM tracking |
| Pipeline for Flagship | 30+ warm leads | CRM tracking |